## Slide 1
Task-Oriented Deep Joint Source–Channel Coding
Semantic communication for bandwidth-constrained image classification
The project studies whether an edge device can send the information needed for a classification task without having to transmit and reconstruct every image detail.
Capstone First Review
Review window: 18–22 August 2026
Presentation slot: 15 minutes
Team and guide details to be added
Rubric: Motivation, Objectives
First Review · 18–22 August 2026
1 / 12

## Slide 2
The project in one minute
1
Observe
An edge camera sees an image.
2
Send
The link has limited bandwidth and added noise.
3
Decide
A receiver predicts the image class.
4
Compare
We measure task accuracy at the same channel budget.
Semantic communication
Send the information required to complete the task. Reconstructing every original pixel is optional when the task does not need it.
The final result is classification accuracy after transmission, not image quality by itself.
Rubric: Motivation, Objectives
Tier 1 is a simulation-first image-classification experiment
2 / 12

## Slide 3
How a conventional image link solves the task
Image
camera input
Compress
JPEG 2000
Protect bits
LDPC + modulation
Add noise
simulated channel
Recover and classify
image → class label
Compression
reduces the number of source bits.
Error correction
adds controlled redundancy so damaged bits can be recovered.
Modulation
maps protected bits to symbols sent through the channel.
Classifier
uses the recovered image to choose a class label.
Limitation: each stage is designed mainly to recover images and bits, while the final metric is whether the class decision is correct.
Rubric: Motivation, Subject Knowledge
Headline baseline: JPEG 2000 + TS 38.212-derived LDPC over AWGN
3 / 12

## Slide 4
What the learned joint system changes
Image
sender input
Neural encoder
learned representation
Noisy channel
used during training
Neural decoder
recover task information
Class
receiver output
The central change
The sender and receiver are trained together through the channel. The transmitted representation can therefore preserve information useful for classification after noise.
Why not send the label?
The project fixes the deployment split: the sender has an encoder, while the receiver owns the decoder and classifier. Sending a label would move the full task model to the sender and test a different system.
The method is supervised end-to-end learning. It is not reinforcement learning and it does not use an LLM.
Rubric: Motivation, Objectives, Subject Knowledge
DJSCC = deep joint source–channel coding
4 / 12

## Slide 5
Why the comparison needs three systems
System
What it sends
What the comparison tells us
Classical image link
A compressed image protected by LDPC and modulation.
How a strong conventional separated system performs.
Digital feature control
Quantized learned features through the same digital physical layer.
Whether task-aware representation alone explains an improvement.
Learned joint link
A continuous representation learned together with the noisy channel.
Whether joint source–channel learning adds further value.
Research question
At the same bandwidth and channel conditions, can the learned joint system preserve classification accuracy better than the tuned classical system, and is any difference specifically consistent with joint coding?
Rubric: Objectives, Subject Knowledge
The third system separates task awareness from joint coding
5 / 12

## Slide 6
What prior research establishes—and leaves open
Short-packet communication
Finite packets pay coding overhead and can fail abruptly.
Measure the practical baseline instead of assuming ideal capacity. [1–4]
Learned image compression
Neural transforms can improve rate–distortion performance.
Good reconstruction quality is not the same as good task accuracy. [11–17]
DeepJSCC
Learned continuous mappings can degrade gradually under noise.
Most image studies emphasize reconstruction rather than classification. [5–10,24]
Task-oriented communication
Learned features can preserve inference under link limits.
Task awareness and joint coding are often not isolated from each other. [18–23]
Gap addressed
A fair three-way comparison for image classification at equal channel use, with failures retained and one sealed test campaign.
Rubric: Problem Survey, Subject Knowledge
30-source synthesis: docs/literature-review.md
6 / 12

## Slide 7
How one image becomes one fair comparison
Held equal for all systems
Why the control exists
Same image and dataset split
Prevents easier samples from being assigned to one system.
Same complex-symbol budget
Makes bandwidth use directly comparable.
Same SNR definition and keyed noise
Pairs outcomes under the same channel condition.
Validation-only tuning
Keeps all choices away from the sealed test split.
Every failure stays in the denominator
Prevents failed transmissions from disappearing from accuracy.
Full byte and physical-layer identity
Prevents hidden overhead or missing BLER evidence from helping a system.
The test split remains sealed until gate G-12. No test result exists at First Review.
Rubric: Subject Knowledge, Objectives
SPEC BR-4, BR-10/11 and ER-3/9/10
7 / 12

## Slide 8
What the project will complete and test
Completion objectives
1.
Build all three transmission systems.
2.
Match their communication resources and channel conditions.
3.
Freeze every choice before test access.
4.
Run one paired test campaign and report the result either way.
Preregistered questions
H1
At low SNR, does the learned system outperform the adaptive classical system?
H2
Does a fixed classical configuration show a cliff while the learned system degrades more gradually?
H3
Does the learned–classical gap contract as SNR improves?
H4
Does the learned joint system also exceed the digital feature control?
Completion means executing the protocol correctly. A positive learned-system result is not required.
Rubric: Objectives, Hypothesis
Formal H1 decision rule appears on slide 12 · exact protocol: SPEC §2
8 / 12

## Slide 9
What has been demonstrated so far
Gate
Observed evidence
Plain-language meaning
Boundary
G-1
89.8% validation accuracy
The reference image-classification task is viable.
Validation only; test is sealed.
G-7
1.64 M parameters; measured GPU profile
The planned learned model fits the available GPU.
A feasibility profile, not training.
G-2
Golden vectors and BLER conformance pass
The digital physical-layer implementation behaves as expected.
Small conformance evidence, not the full table.
W4
Bounded conventional pipeline runs end to end
Compression, coding, channel, decoding and records are integrated.
Integration evidence, not a comparison result.
G8_C
C2 characterization paused at a durable checkpoint
Full-strength BLER measurement can resume safely.
Table, selection and training are unfinished.
No worker is running. No selection, training, validation decoding or test access has occurred.
Rubric: Subject Knowledge
Engineering and gate evidence only · no learned-versus-classical result
9 / 12

## Slide 10
What remains after First Review
Stage
State
Work
Output
G8_C → G-8
Paused → planned
Finish BLER characterization; freeze the table; select classical operating points.
Frozen baseline
W5–W8
Planned
Train DJSCC and calibrate the task/reconstruction objective.
Frozen learned model
W9
Planned
Build and verify the task-aware digital feature control.
Attribution control
W10–W12
Planned
Validation rehearsal; freeze all choices; run one sealed test campaign.
Hypothesis decisions
W13–W17
Planned
Prepare demo, report, poster and final review package.
Final submission
First Review: 18–22 Aug · Second Review: 29 Sep–3 Oct · Final Review: 17–21 Nov · Report due: 20 Nov
W16 is report contingency, not room for new experimental scope.
Rubric: Time Plan
docs/gantt-plan.md · unfinished stages remain marked unfinished
10 / 12

## Slide 11
What this First Review should confirm
Research boundary
Compare the three systems on image classification over normalized AWGN at matched complex-symbol budgets, using one sealed test campaign.
Technical claim boundary
The conventional path uses OpenJPEG 2.5.4 and TS 38.212-derived LDPC/rate matching. The project does not claim a complete 5G NR radio link.
Deployment boundary
Simulation-first Tier 1 is the required path. Conducted SDR replay and edge-device deployment remain optional stretch work after G-5.
Decision requested
Confirm the task definition, the three-system comparison, the fairness controls and simulation-first Tier 1 as a sufficient capstone scope.
Outstanding human item: record the guide's dated acknowledgement of the no-required-hardware path.
Rubric: Objectives, Subject Knowledge
PR-3 standards register · PR-9 deployment dossier · acknowledgement PENDING
11 / 12

## Slide 12
Formal H1 rule and First Review coverage
H1 — low-SNR separation (confirmatory primary)
Comparator: learned versus classical_adaptive at the headline ratio. A grid point qualifies when the studentized paired mean √N·Δ̂(s)/σ̂(s) exceeds 1.96. Let R_obs be the longest run of consecutive qualifying points at or below the training SNR. H1 is supported only if R_obs ≥ 3 and the calibrated run p-value ≤ 0.05.
The run rule decides H1. The mean paired accuracy difference over the full low-SNR region is the effect size of record. A curve crossing is reported if observed but is not required.
Outcome rule: support, no support, or an adverse result are all valid project findings. The protocol does not change after test access.
Six-criterion rubric map
Motivation
2–4
Objectives
1–2, 5, 8, 11
Hypothesis
8, 12
Problem Survey
6
Subject Knowledge
3–7, 9, 11–12
Time Plan
10
Backing evidence: 30-source literature review, corrected Gantt, standards register, deployment dossier and authenticated gate records.
Rubric: Motivation, Objectives, Hypothesis, Problem Survey, Subject Knowledge, Time Plan
Exact protocol: SPEC §2 · full survey: docs/literature-review.md
12 / 12