## Slide 1
Task-Oriented Deep Joint Source–Channel Coding
Semantic communication for bandwidth-constrained image classification
The project studies whether an edge device can send the information needed for a classification task without having to transmit and reconstruct every image detail.
Capstone First Review
Review window: 18–22 August 2026
Presentation slot: 15 minutes
Team and guide details to be added
Rubric: Motivation, Objectives
First Review · 18–22 August 2026
1 / 12

## Slide 2
The project in one minute
1
Observe
An edge camera sees an image.
2
Send
The link has limited bandwidth and added noise.
3
Decide
A receiver predicts the image class.
4
Compare
We measure task accuracy at the same channel budget.
Semantic communication
Send the information required to complete the task. Reconstructing every original pixel is optional when the task does not need it.
The final result is classification accuracy after transmission, not image quality by itself.
Rubric: Motivation, Objectives
Tier 1 is a simulation-first image-classification experiment
2 / 12

## Slide 3
How a conventional image link solves the task
Image
camera input
Compress
JPEG 2000
Protect bits
LDPC + modulation
Add noise
simulated channel
Recover and classify
image → class label
Compression
reduces the number of source bits.
Error correction
adds controlled redundancy so damaged bits can be recovered.
Modulation
maps protected bits to symbols sent through the channel.
Classifier
uses the recovered image to choose a class label.
Limitation: each stage is designed mainly to recover images and bits, while the final metric is whether the class decision is correct.
Rubric: Motivation, Subject Knowledge
Headline baseline: JPEG 2000 + TS 38.212-derived LDPC over AWGN
3 / 12

## Slide 4
What the learned joint system changes
Image
sender input
Neural encoder
learned representation
Noisy channel
used during training
Neural decoder
recover task information
Class
receiver output
The central change
The sender and receiver are trained together through the channel. The transmitted representation can therefore preserve information useful for classification after noise.
Why not send the label?
The project fixes the deployment split: the sender has an encoder, while the receiver owns the decoder and classifier. Sending a label would move the full task model to the sender and test a different system.
The method is supervised end-to-end learning. It is not reinforcement learning and it does not use an LLM.
Rubric: Motivation, Objectives, Subject Knowledge
DJSCC = deep joint source–channel coding
4 / 12

## Slide 5
What prior research establishes—and leaves open
Short-packet communication
Finite packets pay coding overhead and can fail abruptly.
Measure the practical baseline instead of assuming ideal capacity. [1–4]
Learned image compression
Neural transforms can improve rate–distortion performance.
Good reconstruction quality is not the same as good task accuracy. [11–17]
DeepJSCC
Learned continuous mappings can degrade gradually under noise.
Most image studies emphasize reconstruction rather than classification. [5–10,24]
Task-oriented communication
Learned features can preserve inference under link limits.
Task awareness and joint coding are often not isolated from each other. [18–23]
Gap addressed
A fair three-way comparison for image classification at equal channel use, with failures retained and one sealed test campaign.
Rubric: Problem Survey, Subject Knowledge
30-source synthesis: docs/literature-review.md
5 / 12

## Slide 6
Problem statement and project objectives
Problem statement
Conventional image links protect reconstructed images and bits, while the receiver ultimately needs a correct class decision. A learned joint system may use the limited channel more effectively for that task, but the comparison must isolate task awareness from joint coding.
Research question
At the same bandwidth and channel conditions, can the learned joint system preserve classification accuracy better than a tuned conventional system, and is any remaining difference consistent with joint coding?
Objectives
1.
Build the conventional image, digital feature and learned joint systems.
2.
Match channel use, SNR, image identity and noise across all systems.
3.
Freeze every model and operating choice before opening the test split.
4.
Run one paired test campaign and report positive, null or adverse findings.
Completion depends on executing the fixed protocol correctly, not on obtaining a favorable result.
Rubric: Motivation, Objectives
Objectives are stated as completion work, not promised outcomes
6 / 12

## Slide 7
Proposed methodology and comparison design
Shared input for every arm: same image · same dataset split · same complex-symbol budget · same SNR · same keyed noise
System
Transmission path
Scientific role
Classical image
JPEG 2000 → framing → LDPC → modulation → AWGN → image → classifier
Strong conventional reference
Digital feature
Learned features → quantization → same digital physical layer → task head
Separates task awareness from joint coding
Learned joint
Neural encoder → power normalization → AWGN → neural decoder and class head
Tests end-to-end joint coding
Evaluation controls
Tune on validation only; freeze before test access; retain failed transmissions in accuracy; count all bytes and physical-layer identities; compare paired per-image outcomes.
The test split remains sealed until gate G-12. No test result exists at First Review.
Rubric: Objectives, Subject Knowledge
Three systems · one shared task, resource budget and channel definition
7 / 12

## Slide 8
Hypotheses and evaluation plan
H1 — low-SNR separation (confirmatory primary)
Comparator: learned versus classical_adaptive at the headline ratio. A grid point qualifies when the studentized paired mean √N·Δ̂(s)/σ̂(s) exceeds 1.96. Let R_obs be the longest run of consecutive qualifying points at or below the training SNR. H1 is supported only if R_obs ≥ 3 and the calibrated run p-value ≤ 0.05.
The whole low-SNR-region mean paired difference is the effect size of record. A curve crossing is reported if observed but is not required.
H2
Does a fixed conventional configuration show a cliff while the learned system degrades more gradually?
H3
Does the learned–classical accuracy gap contract as SNR improves?
H4
Does the learned joint system also exceed the task-aware digital feature control?
Outcome rule: support, no support or an adverse result are all valid findings. The protocol does not change after test access.
Rubric: Hypothesis, Subject Knowledge
Exact preregistered protocol: SPEC §2
8 / 12

## Slide 9
What has been demonstrated so far
Gate
Observed evidence
Plain-language meaning
Boundary
G-1
89.8% validation accuracy
The reference image-classification task is viable.
Validation only; test is sealed.
G-7
1.64 M parameters; measured GPU profile
The planned learned model fits the available GPU.
A feasibility profile, not training.
G-2
Golden vectors and BLER conformance pass
The digital physical-layer implementation behaves as expected.
Small conformance evidence, not the full table.
W4
Bounded conventional pipeline runs end to end
Compression, coding, channel, decoding and records are integrated.
Integration evidence, not a comparison result.
G8_C
C2 characterization paused at a durable checkpoint
Full-strength BLER measurement can resume safely.
Table, selection and training are unfinished.
No worker is running. No selection, training, validation decoding or test access has occurred.
Rubric: Subject Knowledge
Engineering and gate evidence only · no learned-versus-classical result
9 / 12

## Slide 10
What remains after First Review
Stage
State
Work
Output
G8_C → G-8
Paused → planned
Finish BLER characterization; freeze the table; select classical operating points.
Frozen baseline
W5–W8
Planned
Train DJSCC and calibrate the task/reconstruction objective.
Frozen learned model
W9
Planned
Build and verify the task-aware digital feature control.
Attribution control
W10–W12
Planned
Validation rehearsal; freeze all choices; run one sealed test campaign.
Hypothesis decisions
W13–W17
Planned
Prepare demo, report, poster and final review package.
Final submission
First Review: 18–22 Aug · Second Review: 29 Sep–3 Oct · Final Review: 17–21 Nov · Report due: 20 Nov
W16 is report contingency, not room for new experimental scope.
Rubric: Time Plan
docs/gantt-plan.md · unfinished stages remain marked unfinished
10 / 12

## Slide 11
Application, scope and project risks
Real-world application
Remote cameras and edge sensors may need to support classification when bandwidth, latency or link reliability is limited. The receiver-owned task model represents split edge/cloud inference.
Required project scope
Tier 1 is a simulation-based comparison of all three systems over normalized AWGN, with matched resources and one sealed test campaign. This is sufficient without radio hardware.
Main risks and controls
BLER work is incomplete: resume from the authenticated checkpoint. A hypothesis may not be supported: report the result without retuning. Hardware adds confounders: keep it as gated stretch work.
Technical claim boundary
OpenJPEG 2.5.4 and TS 38.212-derived LDPC/rate matching over abstract AWGN. The project does not claim a complete 5G NR radio link.
Outstanding human item: the guide's dated acknowledgement of the no-required-hardware path remains pending.
Rubric: Motivation, Subject Knowledge, Objectives
Circular clause 5 · PR-3 standards register · PR-9 deployment dossier
11 / 12

## Slide 12
Review 1 summary and requested decisions
Project summary
Problem
Remote classification must operate over a limited noisy link.
Proposal
Train a task-aware joint encoder and decoder, then compare it with two matched digital systems.
Readiness
The reference task, model feasibility, digital physical layer and conventional pipeline have passed their current gates.
Next work
Finish characterization and selection, train the learned systems, freeze choices, then run the test campaign once.
Six-criterion rubric map
Motivation
2–4, 6, 11
Objectives
6–7, 11–12
Hypothesis
8
Problem Survey
5
Subject Knowledge
3–5, 7–9, 11
Time Plan
10
Decision requested
Confirm the research question, the three-system methodology, the fairness controls, the completion objectives and simulation-first Tier 1 as the project basis.
Rubric: Motivation, Objectives, Hypothesis, Problem Survey, Subject Knowledge, Time Plan
Full package: deliverables/review-1/first-review-package.md
12 / 12